## Sheet1
Committed Backlog Items | Not Started | In Progress | Completed
Fix Project 1 Bugs: As an election official, I want the null pointer bug to be fixed in the plurality algorithm because we can't do updates until that code is fixed. Acceptance and Done Criteria: All unit and system tests run without a null pointer exception. Effort: Medium | - Identify cause of null pointer exception - Resolve error through new code - Rerun unit and system tests
Remove Invalidated Ballots: As an election official, I want the software to determine which ballots are invalidated because the parameters for STV Election ballot validation have become more stringent. Acceptance and Done Criteria: Unit and system tests indicate that invalid ballots have been found. Effort: Small | - Write code for invalidator method - Create new unit tests for Ballot Generator - Create new test logs - Update Java docs
Report for Invalidated Ballots: As an election official, I want the invalidated ballots to be shown in a report for auditability. Acceptance and Done Criteria: A report is successfully generated when invalid ballots are given to an STV election. Effort: Small | - Design report - Code function to write to output file - Create new unit tests - Update Java docs
File Selection GUI: As an election official, I want the system to use a graphical user interface to select files from a directory structure. Acceptance and Done Criteria: Users are able search and select a file from a directory structure GUI Effort: Small | - Research file selection GUI - Code file selection dialogue - Plan manual testing - Complete manual testing - Update Java docs