## Sheet1
Committed Backlog Items | Not Started | In Progress | Completed
Fix Project 1 Bugs: As an election official, I want the null pointer bug to be fixed in the plurality algorithm because we can't do updates until that code is fixed. Acceptance and Done Criteria: All unit and system tests run without a null pointer exception. Effort: Medium |  | - Resolve error through new code (Zac) - Rerun unit and system tests (Zac) | - Identify cause of null pointer exception (Zac)
Remove Invalidated Ballots: As an election official, I want the software to determine which ballots are invalidated because the parameters for STV Election ballot validation have become more stringent. Acceptance and Done Criteria: Unit and system tests indicate that invalid ballots have been found. Effort: Small | - Create new test logs - Update Java docs | - Write code for invalidator method (Isabel) - Create new unit tests for Ballot Generator (isabel)
Report for Invalidated Ballots: As an election official, I want the invalidated ballots to be shown in a report for auditability. Acceptance and Done Criteria: A report is successfully generated when invalid ballots are given to an STV election. Effort: Small | - Create new unit tests - Update Java docs | - Come up with report design(Ian) - Write code to output to report file(Ian)
File Selection GUI: As an election official, I want the system to use a graphical user interface to select files from a directory structure. Acceptance and Done Criteria: Users are able search and select a file from a directory structure GUI Effort: Small | - Plan manual testing - Complete manual testing - Update Java docs | - Research file selection GUI (Jess) - Code file selection dialogue (Jess)