## Sheet1
Committed Backlog Items | Not Started | In Progress | Completed
Fix Project 1 Bugs: As an election official, I want the null pointer bug to be fixed in the plurality algorithm because we can't do updates until that code is fixed. Acceptance and Done Criteria: All unit and system tests run without a null pointer exception. Effort: Medium |  | - Update the BallotGenerator test logs (Zac) | - Identify cause of null pointer exception (Zac) - Resolve error through new code (Zac) - Rerun unit and system tests (Zac) - Rewrite createSTVBallotsTest in Ballot Generator that fails (Zac)
Remove Invalidated Ballots: As an election official, I want the software to determine which ballots are invalidated because the parameters for STV Election ballot validation have become more stringent. Acceptance and Done Criteria: Unit and system tests indicate that invalid ballots have been found. Effort: Small | - Update Java docs | - Add an election with invalid ballots to STV system test (Isabel) | - Write code for invalidator method (Isabel) - Create new test logs (Isabel) - Create new unit tests for Ballot Generator (Isabel)
Report for Invalidated Ballots: As an election official, I want the invalidated ballots to be shown in a report for auditability. Acceptance and Done Criteria: A report is successfully generated when invalid ballots are given to an STV election. Effort: Small | - Create new test logs | - Create new unit tests (Ian) | - Come up with report design(Ian) - Write code to output to report file(Ian) - Update Java docs (Ian)
File Selection GUI: As an election official, I want the system to use a graphical user interface to select files from a directory structure. Acceptance and Done Criteria: Users are able search and select a file from a directory structure GUI Effort: Small | - Complete manual testing - Create new test logs | - Plan manual testing (Jess) - Update Java docs (Jess) | - Research file selection GUI (Jess) - Code file selection dialogue (Jess)